## Sheet1
www.goodoldmanoj.com
Burn down chart Markombur Team
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
ScrumMaster1_ImmanuelSembiring | Pengumpulan data | Pengumpulan data olahraga yang disukai | 2 | 0 | 1 | 0 | 0 | 0 |  |  |  | 3 | 3
|  | membuat sebuah rangkuman olahraga | 1 | 1 | 3 | 0 | 0 | 0 |  |  |  | 2 | 1
|  | mengirimkan gambar untuk slide | 1 | 0 | 3 | 0 | 0 | 0 |  |  |  | 3 | 0
ScrumMaster2_RidikOnriSitindaon | Experimen github | mencoba untuk mengirim file word ke github | 2 | 1 | 8 | 0 | 0 | 0
|  | mencoba untuk mengedit dengan anggota lain | 4 | 2 | 8 | 0 | 0 | 0
|  | Tahap awal pembuatan slide | 5 | 3 | 9 | 0 | 0 | 0 |  |  |  | 4 | 6
ScrumMaster3_StevenRendyMPakpahan | Mengisi logbook | mengisi progress kegiatan | 2 | 4 | 5 | 0 | 0 | 0 |  |  |  | 4 | 5
|  | menambahi isi di dalam slide | 3 | 2 | 3 | 1 | 0 | 0 |  |  |  | 7 | 9
ScrumMaster4_HisarRonaldSaragi | Mempercantik Slide | Menambah isi di dalam slide | 7 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7 | 6
|  | mempercantik slide | 3 | 1 | 8 | 8 | 8 | 8 |  |  |  | 3 | 2
Ideal - Remaining efforts in uninterrupted working hours |  |  | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 30 | 14 | 48 | 9 | 8 | 8 | 0 | 0 | 0 | 33 | 32
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered